## Report_2_&_3
Parse | Parse ID | Parse Name | Owner | Stakeholder | Plan Start | Plan End | Actual Start | Actual End | Status | Delay Reason | Pending At | New ETA | Comment
Parse 1 | P1 | Requirement Gathering | Nghĩa,Vinh | Fiona, Serverus | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | Done
Parse 2 | P2 | Create BI view and Grant permission | Stan | Nghia, Vinh, Kelly | 2025-12-19 | 2025-12-26 | 2025-12-19 | 2025-01-06 | Done | 26-Dec: Stan is working 02-Jan: Fiona and Nghia is working | Fiona, Nghia | 2026-01-09 | New Year Holidays
Parse 3 | P3 | Create dashboard (draft) | Nghĩa | Fiona, Serverus | 2025-12-26 | 2025-12-29 | 2026-01-08 | 2026-01-08 | Done
Parse 4 | P4 | Feedback dashboard (draft) | Fiona, Serverus | Nghĩa | 2025-12-29 | 2026-01-03 | 2026-01-09 | 2026-01-16 | Done
Parse 5 | P5 | Update dashboard (UAT) | Nghĩa | Fiona, Serverus | 2026-01-03 | 2026-01-05 | 2026-01-08 | 2026-01-09 | Done
Parse 6 | P6 | UAT confirm | Fiona, Serverus | Nghĩa | 2026-01-05 | 2026-01-09 | 2026-01-09 | 2026-01-09 | Done
Parse 7 | P7 | Setting data load to PROD | Stan, James | Nghĩa | 2026-01-09 | 2026-01-16 | 2026-01-19 | 2026-01-26 | Done | 26-Jan: Stan is working on it | Stan, Nghia | 2026-01-28
Parse 8 | P8 | Go live | Nghĩa | - | 2026-01-16 | 2026-01-18 | 2026-01-26 |  | In Progress |  |  | 2026-01-30
Formulas:
Plan Start = [Plan End, row above]
Plan End = Table1[[#This Row],[Plan Start]]+7

## Report_4
Parse Name | Owner | Stakeholder | Plan Start | Plan End | Actual Start | Actual End | Status | Delay Reason | Pending At | New ETA | Comment
Requirement Gathering | Nghĩa,Vinh | Tuyet Phuong,Fiona
Create dashboard (draft) | Nghĩa | Tuyet Phuong,Fiona
Feedback dashboard (draft) | Tuyet Phuong,Fiona | Nghĩa
Update dashboard (UAT) | Nghĩa | Tuyet Phuong,Fiona
UAT confirm | Tuyet Phuong,Fiona | Nghĩa
Setting data load to PROD | Stan, James | Nghĩa
Go live | Nghĩa | -

## Step_Overview (hidden)
Parse | Description | Start | End | Status
Parse 1 | Requirement Gathering | 2025-12-22 | 2025-12-23 | Done

## Issue_Log (hidden)
Issue ID | Related Task | Issue Description | Owner | Status | ETA
1 | T2 | Waiting database permission | IT Team | Open | 05-Dec

## Design DimEmployee (hidden)
EMPLOYEE_ID | EMPLOYEE_GROUP | EMPLOYEE_NAME | JOB_TITLE | CODE_CENTER | TYPE | EMPLOYEE_TYPE | JOINING_DATE | LAST_WD
000003 | OF | Trần Thụy Linh An | Vice President, Human Resources and Strategic Projects | 8732 | Staff | Permanent | 2018-08-13
000001 | OF | Trần Minh Hiền | Vice President, Finance & Accounting | 8782 | Staff | Permanent | 2018-07-16
000004 | OF | Nguyễn Thị Thanh | QMS & Interpreter Supervisor | 6755 | Staff | Permanent | 2018-08-16